## Details
[6 empty] | Paradise Rentals/Wildwave | Block | Parameter
The purpose of this worksheet is to track all of the items that need to be accomplished from the time a client signs a contract to the time the client’s web site goes live. Each item requires a person responsible, an expected completion date and an actual completion date.
HeaderBegin
| Project | Paradise Rentals/Wildwave |  | Optional Parameters |  |  | Header
| Project Manager | Kenny |  |  |  |  | Header
| Start Work Date | [5 empty] | Header
| Tentative Go Live Date | 2013-01-11 |  |  |  |  | Header
| URL | [5 empty] | Header
| Overall Description | New FullEdit Client |  |  |  |  | Header
| Next Due Date | 2013-03-29 | Next Task | Bob: Contact client to proceed with training |  |  | Header
| Status Notes | 4/5: Need to get up & Running! Other tasks necessary, including importing contact list. 3/12: Lauren will be entering content. May need training in new system. When done we will make new system live. Joe has things in hand. 2/27: Launched. Need to get paid. At some point need to train them. Offered to import mailing list into fullEdit. Not particularly responsive. |  |  |  |  | Header
HeaderEnd
Task |  | Responsible | Expected Date | % Complete | Actual Date | Trak | MainBegin | Completed
Contract Signed & Scanned |  |  |  | 100% |  |  | Contract | TRUE
Domain Questionnaire Sent |  |  |  | 100% |  |  |  | TRUE
Domain Questionnaire Received |  |  |  | 100% |  |  |  | TRUE
Domains Under CMS Control |  |  |  | 100% |  |  |  | TRUE
E-Mail Setup (If Necessary) |  | n/a |  |  |  |  | EMail | TRUE
DNS Servers Set Up |  | Kenny | [5 empty] | FALSE
Design Questionnaire Sent |  |  |  | N/A |  |  |  | FALSE
Discuss Design Questionnaire with Client |  |  |  | 100% |  |  |  | TRUE
Design Questionnaire Received |  |  |  | N/A |  |  |  | FALSE
Source Graphics Received |  | Kenny |  | 10% |  |  |  | FALSE
Graphic Design |  | Natalie |  | 100% |  |  |  | TRUE
Send Graphics mockup to client for approval |  |  |  | 100% |  |  |  | TRUE
Client Approval for Mockup |  |  |  | Approved |  |  |  | FALSE
Content Received |  | Kenny |  | 85% |  |  |  | FALSE
fullEdit Development Site Created |  | Ben |  | 100% | 2013-01-17 |  |  | TRUE
Site Design: CSS, Graphic Layout, etc. |  | Andrew |  | 100% |  |  |  | TRUE
Page Tree Laid Out in Dev Site |  | Andrew |  | 100% |  |  |  | TRUE
Shopping Cart Merchandise Acct Setup |  | Bob |  |  |  |  | ShoppingCart | FALSE
Shopping Cart Styling |  | Andrew |  | 100% |  |  | ShoppingCart | TRUE
Certificate procured (Shopping Cart) |  | Natalie |  | 100% |  |  | ShoppingCart | TRUE
Posts Controller Setup (If Necessary) |  | n/a |  |  |  |  | PostsController | TRUE
Calendar Tool |  | Kenny |  | 100% |  |  | CalendarTool | TRUE
Pages built per contract |  | Kenny |  | 100% |  |  |  | TRUE
May need to train Lauren |  | Joe | [5 empty] | FALSE
Move to new system. | [6 empty] | Custom | FALSE
[7 empty] | Custom | FALSE
Customer testing and Approval |  | Kenny |  | 100% |  |  |  | TRUE
MainEnd
| Current Impediments | [6 empty] | Impediment
Date | Issue & Notes |  |  |  | Resolved |  | ImpedimentBegin
[7 empty] | Impediment1 | FALSE
[7 empty] | Impediment2 | FALSE
[7 empty] | Impediment3 | FALSE
ImpedimentEnd
Note on A13: Task to be Completed
Note on C13: Person Responsible For This Task Enter "n/a" if this task is not needed for this project.
Note on D13: Expected Completion Date For This Task
Note on E13: Approximate Percent Completed. Please use actual percentages, rather than words.
Note on F13: Actual Date Task Was Completed. Please do fill this in when done.
Note on G13: Corresponding Trak Ticket Number, if available.
Note on B42: Any issues that are preventing this project from moving forward. Delete rows from here when the impediment no longer exists.
Note on A43: Date Impediment Noted
Note on B43: Nature of Impediment and any notes describing it's causes or attempts at resolultion
Note on F43: Date Impediment Resolved.
Note on A14: The scan of the contract's signature page should be stored in the Client's folder.
Note on B9: Overview of the Project
Note on B8: Project Development URL
Note on B10: Next important due date and task
Note on B11: General notes about the project. This is a free form field. Include as much info as needed and expand the row as necessary.
Note on E4: Check optional items that are necessary for this project.

## Data (hidden)
Client Data
Please note that this sheet is formatted so that the master spreadsheet can read it
Please don't make any changes to this sheet. Make any changes to the Details sheet.
Most changes made there will be reflected here.
Category | FieldName | Value | Parameters
Header | ProjectType | Full Edit Setup
Header | Version | 0.7
Header | ProjectName | Paradise Rentals/Wildwave
Header | ProjectManager | Kenny
Header | StartDate
Header | EndDate | 2013-01-11
Header | URL
Header | Description | New FullEdit Client
Header | NextDueDate | 2013-03-29
Header | NextTask | Bob: Contact client to proceed with training
Header | StatusNotes | 4/5: Need to get up & Running! Other tasks necessary, including importing contact list. 3/12: Lauren will be entering content. May need training in new system. When done we will make new system live. Joe has things in hand. 2/27: Launched. Need to get paid. At some point need to train them. Offered to import mailing list into fullEdit. Not particularly responsive.
Options | Email | FALSE
Options | ShoppingCart | TRUE
Options | CMS-EBlast | TRUE
Options | PostsController | FALSE
Options | Calendar | TRUE
Options | Custom | FALSE
|  |  | Task | Due Date | Responsible
Main | NextTask1 | Kenny: DNS Servers Set Up | DNS Servers Set Up | 0 | Kenny
Main | NextTask2 | not implimented yet
Impediments | Impediment1
Impediments | Impediment2 | not implimented yet
Impediments | Impediment3 | not implimented yet